## Timeline
[42 empty] | Leader | Duration | Partner 1 |  | Partner 2 |  | Partner 3
|  | Duration | Start | End | Predecessor | 15 |  | 16 | [11 empty] | 17 | [11 empty] | 18
ID | Task Name |  |  |  |  | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 |  |  | jp | pm | jp | pm | jp | pm
1 | WP1 Project Management | 42 | 1 | 42 |  | 15 11 1: WP1 | Partner 1 | 36 |  | 15 |  | 1 |  | 4
2 | T1.1 Project Coordination and Monitoring | 2 | 1 | 2 | [37 empty] | Partner 1 | 36 | 0.2 | 7.2 | 0 | 0 | 0.05 | 1.8 | bar: 15 11 1 to 18 10 36
3 | T1.2 Project Reporting | 42 | 1 | 42 | [37 empty] | Partner 2 | 36 | 0.2 | 7.2 | 0 | 0 | 0.05 | 1.8 | bar: 15 11 1 to 18 10 36
4 | T1.3 Quality Assurance & Risk Management | 42 | 1 | 42 | [37 empty] | Partner 3 | 10 | 0.05 | 0.5 | 0.1 | 1 | 0 | 0 | bar: 15 11 1 to 15 12 2; 16 4 6; 16 8 10; 16 12 14; 17 4 18; 17 8 22; 17 12 26; 18 4 30; 18 8 34
5 | WP2 xxx | 5 | 1 | 5 | [38 empty] | 31 |  | 0 |  | 0 |  | 0
6 | [42 empty] | 0 |  | 0 |  | 0 |  | 0
7 | [42 empty] | 0 |  | 0 |  | 0 |  | 0
8 |  | 2 | 1 | 2 | [38 empty] | 0 |  | 0 |  | 0 |  | 0
9 |  | 1 | 3 | 3 | 10 | [37 empty] | 0 |  | 0 |  | 0 |  | 0
10 | WP3 yyy | 7 | 5 | 11 | [38 empty] | 35 |  | 0 |  | 0 |  | 0
11 | [42 empty] | 0 |  | 0 |  | 0 |  | 0
12 |  | 2 | 1 | 2 | [38 empty] | 0 |  | 0 |  | 0 |  | 0
13 | [42 empty] | 0 |  | 0 |  | 0 |  | 0
14 | WP4 zzz | 11 | 10 | 20 | [38 empty] | 36 |  | 0 |  | 0 |  | 0
15 |  | 1 | 10 | 10 | 15 | [37 empty] | 0 |  | 0 |  | 0 |  | 0
16 |  | 1 | 11 | 11 | 21 | [37 empty] | 0 |  | 0 |  | 0 |  | 0
17 | [42 empty] | 0 |  | 0 |  | 0 |  | 0
18 |  | 4 | 12 | 15 | [38 empty] | 0 |  | 0 |  | 0 |  | 0
19 |  | 2 | 13 | 14 | 24 | [37 empty] | 0 |  | 0 |  | 0 |  | 0
20 | WP5 Dissemination & Exploation | 42 | 1 | 42 | [38 empty] | 36 |  | 0 |  | 0 |  | 0
21 |  | 2 | 1 | 2 | [38 empty] | 0 |  | 0 |  | 0 |  | 0
22 |  | 40 | 3 | 42 | 61 | [37 empty] | 0 |  | 0 |  | 0 |  | 0
23 |  | 2 | 1 | 2 | [38 empty] | 0 |  | 0 |  | 0 |  | 0
24 |  | 2 | 3 | 4 | 63 | [37 empty] | 0 |  | 0 |  | 0 |  | 0
25 | [42 empty] | 0 |  | 0 |  | 0 |  | 0
26 |  | 38 | 5 | 42 | 61;64 | [37 empty] | 0 |  | 0 |  | 0 |  | 0
27 | [42 empty] | 0 |  | 0 |  | 0 |  | 0
28 | [42 empty] | 0 |  | 0 |  | 0 |  | 0
[6 empty] | 18 9 35: Person-month per partner |  |  |  | 15 |  | 1 |  | 4
Note on AS5: Pavel Čech: průměrný počet úvazků za dobu trvání úkolu
Note on B6: Pavel Čech: balíček pro řízení projektu - zpravidla v každém projektu
Note on B25: Pavel Čech: balíček zaměřený na propagaci a široké využití výsledků projektu - bývá zpravidla u každého projektu

## Total
| UHK | MU | TUE
Total person-month | 15 | 1 | 4
Salary per month | 1600 | 8975 | 5000
Total personal cost | 24000 | 8975 | 20000
Travel | 25000 | 25000 | 25000
Equipment
Other goods and services | 1000 | 1000 | 10000
Other direct costs | 26000 | 26000 | 35000
Direct cost of subcontracting | 0 | 0 | 0
Indirect cost | 12500 | 8743.75 | 13750
Total amount | 62500 | 43718.75 | 68750 | 174968.75
Note on B4: Pavel Čech: Averaged salary rate
Note on B6: Pavel Čech: travel costs and related subsistence
Note on B8: Pavel Čech: e.g. consumables and supplies, dissemination (including open access), protection of results, certificates on the financial statements, certificates on the methodology, translations and publications

## WP
Indexy |  | 1 | 5 | 10 | 14 | 20
|  | WP1 | WP2 | WP3 | WP4 | WP5 | Total
2 | Partner 1 | 15 | 0 | 0 | 0 | 0 | 15
4 | Partner 2 | 1 | 0 | 0 | 0 | 0 | 1
6 | Partner 3 | 4 | 0 | 0 | 0 | 0 | 4
| Total | 20 | 0 | 0 | 0 | 0 | 20

## Partner 1
Justification
Total person-month | 15
Salary per month | 1600
Total personal cost | 24000
Travel | 25000 | e.g. 10 cooperation meetings (2 persons * 10 meetings * 950 EUR = 19 000 EUR), congresses (2 persons * 2 congresses * 1 500 EUR = 6 000 EUR)
Equipment
Other goods and services | 1000
Other direct costs | 26000
Direct cost of subcontracting | 0
Indirect cost | 12500
Total amount | 62500
Note on B4: Pavel Čech: Averaged salary rate - standard practice in your institution
Note on B6: Pavel Čech: travel costs and related subsistence
Note on B7: Pavel Čech: the call does not allow any investment to equipment
Note on B8: Pavel Čech: e.g. consumables and supplies, dissemination (including open access), protection of results, certificates on the financial statements, certificates on the methodology, translations and publications

## Partner 2
Justification
Total person-month | 1
Salary per month | 8975
Total personal cost | 8975
Travel | 25000 | e.g. 10 cooperation meetings (2 persons * 10 meetings * 950 EUR = 19 000 EUR), congresses (2 persons * 2 congresses * 1 500 EUR = 6 000 EUR)
Equipment
Other goods and services | 1000
Other direct costs | 26000
Direct cost of subcontracting | 0
Indirect cost | 8743.75
Total amount | 43718.75
Note on B4: Pavel Čech: Averaged salary rate - standard practice in your institution
Note on B6: Pavel Čech: travel costs and related subsistence
Note on B7: Pavel Čech: the call does not allow any investment to equipment
Note on B8: Pavel Čech: e.g. consumables and supplies, dissemination (including open access), protection of results, certificates on the financial statements, certificates on the methodology, translations and publications

## Partner 3
Justification
Total person-month | 4
Salary per month | 5000
Total personal cost | 20000
Travel | 25000 | e.g. 10 cooperation meetings (2 persons * 10 meetings * 950 EUR = 19 000 EUR), congresses (2 persons * 2 congresses * 1 500 EUR = 6 000 EUR)
Equipment
Other goods and services | 10000
Other direct costs | 35000
Direct cost of subcontracting | 0
Indirect cost | 13750
Total amount | 68750
Note on B4: Pavel Čech: Averaged salary rate - standard practice in your institution
Note on B6: Pavel Čech: travel costs and related subsistence
Note on B7: Pavel Čech: the call does not allow any investment to equipment
Note on B8: Pavel Čech: e.g. consumables and supplies, dissemination (including open access), protection of results, certificates on the financial statements, certificates on the methodology, translations and publications